# NS-DOPEY-009-IMPLEMENTATION-PLAYBOOK

## Dispensary Implementation Kit (DIK) – gates

Gate 0: Market ruleset + licensing path confirmed

Gate 1: Entity structure + capitalization approved

Gate 2: Site selected + security plan drafted

Gate 3: Vendor stack selected + contracts signed

Gate 4: SOPs + training ready; systems configured

Gate 5: Inventory onboarding + dry runs complete

Gate 6: Soft open complete; KPIs stable

Gate 7: Full open; monthly close clean

## Store launch checklist (condensed)

Security system installed + camera retention configured

POS and seed-to-sale connected and tested end-to-end

User access roles provisioned; MFA enabled where supported

Cash controls ready (safes, logs, dual-control procedures)

Training complete: compliance + product + customer experience

Opening week staffing schedule finalized

Incident response binder ready (contacts, procedures, reporting)

## Post-launch stabilization (first 30 days)

Daily variance review (inventory + cash)

Weekly shrink review and corrective actions

Vendor issues triage and fixes

KPI tuning: labor, assortment, promotions, attach rate